## Executive Summary
🔐 GestureSpeak Backend – Security Vulnerability Assessment Report
Assessment Date: June 18, 2026 ¦ Reviewer: Senior Application Security Engineer ¦ Project: GestureSpeak Spring Boot Backend
CRITICAL |  | HIGH |  | MEDIUM |  | LOW | TOTAL
3 |  | 14 |  | 13 |  | 3 | 33
⚠️ OVERALL RISK RATING: CRITICAL – Immediate Remediation Required
Scope |  | Spring Boot 3.3.0 Backend (Java 17) – All controllers, services, configs, and resource files. 8 controllers, 3 services, 3 config files, 1 pom.xml, 1 application.properties, 1 firebase-service-account.json reviewed.
Technology Stack |  | Spring Boot 3.3.0 ¦ Spring Security ¦ Firebase Admin SDK 9.3.0 ¦ Firestore ¦ Twilio ¦ MyMemory Translation API ¦ Google TTS Proxy
Critical Attack Paths |  | 1) Use 'mock-admin-token' → instant ADMIN access to all data 2) Send any bearer token when Firebase is unconfigured → bypass all auth 3) Supply userId in SOS body → trigger SOS on behalf of any user 4) Brute-force 6-digit OTP (no rate limit) → account takeover
Findings by Category
Category | Critical | High | Medium | Low | Total
API Security | 0 | 3 | 3 | 0 | 6
Authentication | 3 | 3 | 2 | 0 | 8
Authorization | 0 | 3 | 1 | 0 | 4
Business Logic | 0 | 0 | 1 | 1 | 2
Infrastructure | 0 | 0 | 1 | 1 | 2
Injection | 0 | 1 | 1 | 0 | 2
Input Validation | 0 | 1 | 2 | 1 | 4
Sensitive Data Exposure | 0 | 3 | 2 | 0 | 5

## Full Findings
Security Findings – Detailed Report
Finding ID | Category | Severity | File Path | Line(s) | Vulnerability Type | CWE | OWASP | Explanation | Affected Endpoint | Recommended Remediation | Priority
AUTH-001 | Authentication | CRITICAL | config/FirebaseTokenFilter.java | 39–46 | Hardcoded Mock Admin Token | CWE-798 | A02:2021 – Cryptographic Failures | A hardcoded secret string 'mock-admin-token' is accepted as a valid admin credential. Any attacker who knows this string gains full ADMIN privileges without a real identity check. | All /api/** routes | Remove hardcoded tokens entirely. Use only real Firebase ID-token verification in all environments. | P1 – Fix Now
AUTH-002 | Authentication | CRITICAL | config/FirebaseTokenFilter.java | 51–55 | Authentication Bypass – Any Token Accepted | CWE-287 | A07:2021 – Identification and Authentication Failures | When Firebase is not properly configured (placeholder credentials), the filter accepts ANY bearer token and derives a uid from its hash. This completely bypasses authentication. | All authenticated endpoints | Fail closed: return HTTP 401/503 when Firebase is not configured rather than granting access. | P1 – Fix Now
AUTH-003 | Authentication | CRITICAL | config/FirebaseTokenFilter.java | 68–74 | Silent Fallback on Token Verification Failure | CWE-755 | A07:2021 – Identification and Authentication Failures | If real Firebase ID-token verification throws an exception (e.g., forged or expired token), the filter silently falls back to granting dev-mode access instead of rejecting the request. | All authenticated endpoints | On verification failure, clear the security context and return HTTP 401. Never fall back to authenticated state. | P1 – Fix Now
AUTH-004 | Authentication | HIGH | config/FirebaseTokenFilter.java | 43–46 | Wildcard Mock-User Token Accepted | CWE-290 | A07:2021 – Identification and Authentication Failures | Any token that starts with 'mock-user-token' is accepted as a valid user. An attacker can craft arbitrary UIDs (e.g., 'mock-user-token-admin-uid') to impersonate any user. | All user-level endpoints | Remove all mock token logic from production code. Gate dev helpers behind a build profile. | P2 – Fix This Sprint
AUTH-005 | Authentication | HIGH | controller/AuthController.java | 172 | Weak OTP – No Rate Limiting / No Expiry | CWE-307 | A07:2021 – Identification and Authentication Failures | The 6-digit OTP for password reset is stored in a plain in-memory map with no expiry and no brute-force protection. An attacker can enumerate all 1,000,000 combinations via repeated API calls. | POST /api/auth/verify-otp | Add OTP expiry (5 min), max 5 attempts, and account lockout. Consider using a secure token instead of numeric OTP. | P2 – Fix This Sprint
AUTH-006 | Authentication | HIGH | controller/AuthController.java | 175–178 | OTP Leaked to Server Logs | CWE-532 | A09:2021 – Security Logging and Monitoring Failures | The OTP code is printed to System.out in plain text. Any log aggregation system, CI runner, or shared console exposes the secret. | POST /api/auth/forgot-password | Never log secrets. Send OTP via a secure email/SMS channel only. | P2 – Fix This Sprint
AUTH-007 | Authentication | MEDIUM | controller/AuthController.java | 71–101 | Self-Asserted Registration – No UID Validation | CWE-346 | A07:2021 – Identification and Authentication Failures | The /register endpoint accepts a client-supplied 'uid' and writes it to Firestore without verifying it belongs to the caller. A user can register under any uid, including an admin's uid. | POST /api/auth/register | Derive uid exclusively from a verified Firebase ID token; never trust client-supplied uid. | P3 – Fix Next Sprint
AUTH-008 | Authentication | MEDIUM | controller/AuthController.java | 196–223 | Password Reset Without OTP Re-Verification | CWE-613 | A07:2021 – Identification and Authentication Failures | The reset-password flow checks the OTP once but does not re-confirm the user's identity before actually changing the Firebase Auth password. A race condition between verify-otp and reset-password could be exploited. | POST /api/auth/reset-password | Use a single-use signed token from the verify step; tie it to the session that completed OTP verification. | P3 – Fix Next Sprint
AUTHZ-001 | Authorization | HIGH | controller/EmergencyController.java | 56–64 | IDOR – getAuthUserId Falls Back to Hardcoded UID | CWE-639 | A01:2021 – Broken Access Control | getAuthUserId() swallows exceptions and returns 'mock-user-uid' on error. If authentication fails silently, all emergency data operations are performed against the hardcoded fallback user's data. | All /api/emergency/** routes | Return HTTP 401 when the principal cannot be resolved. Never fall back to a default uid. | P2 – Fix This Sprint
AUTHZ-002 | Authorization | HIGH | controller/EmergencyController.java | 207–208 | IDOR – Client-Supplied userId in SOS Endpoint | CWE-639 | A01:2021 – Broken Access Control | POST /api/emergency/send-sos accepts a 'userId' field from the request body and uses it to fetch contacts and send SOS alerts. Any authenticated user can trigger SOS on behalf of another user. | POST /api/emergency/send-sos | Ignore client-supplied userId. Always derive uid from the authenticated session. | P2 – Fix This Sprint
AUTHZ-003 | Authorization | HIGH | config/FirebaseTokenFilter.java | 64–65 | Privilege Escalation via Email Match | CWE-269 | A01:2021 – Broken Access Control | Admin role is granted based on a simple email string comparison ('admin@gesturespeak.com'). In the fallback dev mode, any user who registers with that email address gains ADMIN privileges. | POST /api/admin/** | Grant admin via Firebase custom claims only. Never use email-based role assignment. | P2 – Fix This Sprint
AUTHZ-004 | Authorization | MEDIUM | controller/EmergencyController.java | 160–178 | IDOR – Delete Contact Without Ownership Check | CWE-639 | A01:2021 – Broken Access Control | DELETE /api/emergency/contacts/{id} deletes the document with the given id under the current user's subcollection, but in mock mode it removes the contact from any user's list. No validation that the id belongs to the requesting user is performed in Firestore. | DELETE /api/emergency/contacts/{id} | Verify document ownership before deletion; return 403 if the contact does not belong to the requesting user. | P3 – Fix Next Sprint
INJ-001 | Injection | HIGH | controller/TranslationController.java | 67–70 | Server-Side Request Forgery (SSRF) – TTS Endpoint | CWE-918 | A10:2021 – Server-Side Request Forgery | The /api/tts endpoint constructs a URL to Google TTS by embedding user-controlled 'lang' and 'text' parameters. A crafted lang value containing URL fragments could redirect the server request to internal network endpoints. | POST /api/tts | Whitelist allowed language codes. Validate the lang parameter against an enum before constructing the URL. | P2 – Fix This Sprint
INJ-002 | Injection | MEDIUM | service/TranslationService.java | 206–212 | Unvalidated Redirect to External Translation API | CWE-601 | A03:2021 – Injection | User-supplied text and language codes are concatenated into an external API URL without strict allowlisting of language codes. A malformed language code could alter the HTTP request path. | POST /api/translate | Validate src/tgt against a strict whitelist of ISO 639-1 codes before use in URL. | P3 – Fix Next Sprint
INP-001 | Input Validation | HIGH | controller/AuthController.java | 140–141 | Unsanitized Username Logged to Audit Log | CWE-117 | A09:2021 – Security Logging and Monitoring Failures | The 'username' from the request body is logged directly: 'Updated username to: ' + username. A malicious username containing newlines or log-injection characters can forge log entries. | PUT /api/auth/profile | Sanitize log output; strip or escape control characters before logging user input. | P2 – Fix This Sprint
INP-002 | Input Validation | MEDIUM | controller/EmergencyController.java | 123 | Phone Number Sanitization Insufficient | CWE-20 | A03:2021 – Injection | Phone number sanitization only strips non-digit/+ characters. No length or format validation is performed before passing to Twilio, potentially enabling unexpected behavior or Twilio API errors. | POST /api/emergency/contacts | Validate phone numbers against E.164 format using a library such as libphonenumber. | P3 – Fix Next Sprint
INP-003 | Input Validation | MEDIUM | controller/HistoryController.java | 72–76 | No Input Length Limits on Free-Text Fields | CWE-400 | A05:2021 – Security Misconfiguration | The history save endpoint stores 'original' and 'translated' text without any length validation. An attacker can submit megabytes of data per request, exhausting Firestore write quota or JVM heap. | POST /api/history | Enforce max field lengths (e.g., 2000 chars). Return HTTP 400 for oversized input. | P3 – Fix Next Sprint
INP-004 | Input Validation | LOW | controller/AuthController.java | 77–79 | Missing Email Format Validation on Registration | CWE-20 | A03:2021 – Injection | The /register endpoint only checks that 'uid' and 'email' are non-null; it does not validate that the email is a valid email address format. | POST /api/auth/register | Add regex or Bean Validation (@Email) to reject malformed email addresses. | P4 – Backlog
SDE-001 | Sensitive Data Exposure | HIGH | resources/firebase-service-account.json | 1–12 | Service Account Key Committed to Source Code | CWE-312 | A02:2021 – Cryptographic Failures | The Firebase service account JSON (even as a placeholder) is checked into source control. In a real deployment where the real key is substituted, anyone with repo access has full Firebase Admin access. | N/A – Infrastructure | Add firebase-service-account.json to .gitignore. Inject via environment variable or secret manager at runtime. | P2 – Fix This Sprint
SDE-002 | Sensitive Data Exposure | HIGH | controller/HistoryController.java | 123–131 | Sensitive PII Logged to stdout | CWE-532 | A09:2021 – Security Logging and Monitoring Failures | Every translation saves the full original text, translated text, mode, and confidence to System.out. This data may contain private medical or personal communications. | POST /api/history | Remove verbose logging of user content. If logging is needed, use structured masked logging. | P2 – Fix This Sprint
SDE-003 | Sensitive Data Exposure | HIGH | service/TranslationService.java | 185–213 | User Text Exposed in Translation API Logs | CWE-532 | A09:2021 – Security Logging and Monitoring Failures | User text, the full API request URL (including encoded user content), and the full API response are logged to stdout. This exposes private user communications in logs. | POST /api/translate | Log only metadata (language pair, success/failure, latency). Never log user content. | P2 – Fix This Sprint
SDE-004 | Sensitive Data Exposure | MEDIUM | service/TwilioService.java | 31–36 | SOS Message Content Logged to stdout | CWE-532 | A09:2021 – Security Logging and Monitoring Failures | Full SMS message content (including victim location URLs) is printed to stdout during mock dispatch. In any shared log environment this leaks personal location data. | POST /api/emergency/send-sos | Replace content logging with '[SMS dispatched to +XX]'. Do not log message body. | P3 – Fix Next Sprint
SDE-005 | Sensitive Data Exposure | MEDIUM | controller/AuthController.java | 28–48 | Mock Credentials Hardcoded in Production Code | CWE-798 | A02:2021 – Cryptographic Failures | Hardcoded email, uid, and role values for admin and user accounts are embedded in production source code. If mock mode is ever left active, these known credentials allow unauthorized access. | N/A – AuthController constructor | Remove all mock users. Seed test data through a separate test-only configuration class. | P3 – Fix Next Sprint
API-001 | API Security | HIGH | config/SecurityConfig.java | 61 | CORS Wildcard – Allow All Origins | CWE-942 | A05:2021 – Security Misconfiguration | setAllowedOriginPatterns(List.of('*')) combined with setAllowCredentials(true) allows any website to make credentialed cross-origin requests. This can enable CSRF-style attacks from malicious sites. | All endpoints | Restrict allowed origins to specific production and staging domains. Never combine wildcard with allowCredentials=true. | P2 – Fix This Sprint
API-002 | API Security | HIGH | config/SecurityConfig.java | 33 | CSRF Protection Disabled | CWE-352 | A01:2021 – Broken Access Control | CSRF protection is completely disabled. While JWT is used, the CORS wildcard misconfiguration means cookie-based attacks or cross-origin fetch attacks are more viable. | All POST/PUT/DELETE endpoints | If REST-only, CSRF disable is acceptable with strict CORS. Fix the CORS wildcard first. | P2 – Fix This Sprint
API-003 | API Security | HIGH | controller/TranslationController.java | 18 | @CrossOrigin(origins='*') Annotation Overrides Security Config | CWE-942 | A05:2021 – Security Misconfiguration | The TranslationController has a per-controller @CrossOrigin annotation with wildcard origins, overriding the global CORS policy and making these endpoints accessible from any origin. | POST /api/translate, POST /api/tts | Remove per-controller @CrossOrigin. Manage all CORS centrally in SecurityConfig. | P2 – Fix This Sprint
API-004 | API Security | MEDIUM | config/SecurityConfig.java | 46–50 | Missing Security Headers | CWE-693 | A05:2021 – Security Misconfiguration | No security headers are configured: no X-Content-Type-Options, X-Frame-Options, Content-Security-Policy, or Referrer-Policy. This increases exposure to clickjacking and MIME sniffing attacks. | All endpoints | Add a SecurityHeadersFilter or configure headers via Spring Security's headers() DSL. | P3 – Fix Next Sprint
API-005 | API Security | MEDIUM | config/SecurityConfig.java | 31–55 | No Rate Limiting on Any Endpoint | CWE-307 | A05:2021 – Security Misconfiguration | No rate limiting is configured on any endpoint including authentication, OTP verification, SOS dispatch, and translation. This enables brute-force, enumeration, and DoS attacks. | All endpoints especially /api/auth/**, /api/emergency/send-sos | Implement rate limiting via Spring's Resilience4j, Bucket4j, or an API gateway. | P3 – Fix Next Sprint
API-006 | API Security | MEDIUM | config/SecurityConfig.java | 64 | Authorization Header Exposed in CORS | CWE-200 | A02:2021 – Cryptographic Failures | The Authorization header is in exposedHeaders, making the bearer token readable from JavaScript in cross-origin contexts. This can facilitate token theft from third-party scripts. | All endpoints | Remove Authorization from exposedHeaders unless there is a specific business need. | P3 – Fix Next Sprint
BIZ-001 | Business Logic | MEDIUM | controller/EmergencyController.java | 205–283 | SOS Endpoint – No Rate Limiting / Spam Risk | CWE-400 | A05:2021 – Security Misconfiguration | The SOS send endpoint has no rate limiting. An attacker (or broken client) can flood emergency contacts with unlimited SMS messages, causing SMS-flooding abuse of the Twilio account and distress to recipients. | POST /api/emergency/send-sos | Enforce a minimum interval (e.g., 60 s) per user per SOS dispatch. Add rate limiting. | P3 – Fix Next Sprint
BIZ-002 | Business Logic | LOW | controller/AdminController.java | 26–75 | Hardcoded Fake Analytics Data | CWE-807 | A04:2021 – Insecure Design | Admin analytics endpoint returns partially hardcoded statistics (totalPredictions=1432, emergencyAlerts=14). Decisions based on these metrics will be incorrect; it also masks real anomalies. | GET /api/admin/analytics | Derive all statistics from real Firestore aggregation queries. | P4 – Backlog
INF-001 | Infrastructure | MEDIUM | resources/application.properties | 10–12 | Placeholder Twilio Credentials as Defaults | CWE-547 | A05:2021 – Security Misconfiguration | Twilio credentials fall back to literal 'placeholder-*' strings. If environment variables are unset, the app starts silently in mock mode without any error, hiding a misconfiguration. | POST /api/emergency/send-sos | Use required binding (fail-fast on startup if Twilio credentials are missing or placeholder). Log a clear warning. | P3 – Fix Next Sprint
INF-002 | Infrastructure | LOW | pom.xml | 8 | Spring Boot 3.3.0 – Potential Known CVEs | CWE-1104 | A06:2021 – Vulnerable and Outdated Components | Spring Boot 3.3.0 was released in 2024. Newer patch releases (3.3.x) may address security vulnerabilities. The project should be on the latest maintained release. | N/A – Dependency | Update to the latest Spring Boot 3.x patch. Monitor CVE databases for Spring ecosystem vulnerabilities. | P4 – Backlog

## Critical Attack Paths
Critical & High – Exploitable Attack Paths
ATK-1 │ Instant Admin Takeover via Hardcoded Token
1. Attacker sends any request with header: Authorization: Bearer mock-admin-token
2. FirebaseTokenFilter.java line 39: hardcoded string matches → setAuth('mock-admin-uid', true, request)
3. ROLE_ADMIN is granted without any identity verification
4. Attacker calls GET /api/admin/analytics and any future admin endpoints
5. Full admin panel access achieved with zero credentials
💥 Impact: Complete administrative account takeover. Attacker can read all user counts and any data behind ADMIN role.
✅ Fix: Remove hardcoded mock token. Enforce real Firebase verification in all environments.
ATK-2 │ Authentication Bypass – Any Token When Firebase Unconfigured
1. Application deployed with placeholder firebase-service-account.json (current state)
2. FirebaseService.isFirebaseInitialized() returns false
3. Attacker sends any value as Bearer token: e.g., Authorization: Bearer hacked
4. Filter line 54: uid = 'dev-user-' + abs('hacked'.hashCode() % 100000)
5. Attacker is granted ROLE_USER with a deterministic uid
6. Attacker can access all user-level endpoints under that uid
💥 Impact: Full authentication bypass. Every endpoint marked 'authenticated' is publicly accessible.
✅ Fix: Return HTTP 401/503 when Firebase is not configured. Never grant access on unconfigured state.
ATK-3 │ Account Takeover via Unauthenticated OTP Brute-Force
1. Attacker calls POST /api/auth/forgot-password?email=victim@email.com
2. 6-digit OTP generated and stored in ConcurrentHashMap mockOtps
3. No rate limiting, no CAPTCHA, no account lockout on /api/auth/verify-otp
4. Attacker scripts POST /api/auth/verify-otp?email=victim&otp=000000 through 999999
5. Correct OTP found → POST /api/auth/reset-password with new password
6. Victim's Firebase Auth password changed → full account takeover
💥 Impact: Any user account can be taken over. Max 1,000,000 guesses required with no throttle.
✅ Fix: Add OTP expiry (5 min), max 5 attempts per email, exponential backoff, and account lockout.
ATK-4 │ Trigger SOS Alerts on Behalf of Any User (IDOR)
1. Attacker authenticates (even via bypass ATK-2)
2. Attacker sends: POST /api/emergency/send-sos with body {userId: 'victim-uid', ...}
3. Line 207-208: reqUserId is taken from request body if non-empty
4. Victim's emergency contacts are fetched and SMSed
5. Attacker can send unlimited fake SOS alerts on behalf of any user
💥 Impact: SMS spam/harassment of victims' emergency contacts. Twilio credit exhaustion. False emergency dispatches.
✅ Fix: Ignore client-supplied userId. Always use uid from SecurityContextHolder.
ATK-5 │ Impersonate Any User via Mock Token Crafting
1. Attacker knows mock token pattern (visible in source code / GitHub)
2. Attacker sends: Authorization: Bearer mock-user-token-<target-uid>
3. FirebaseTokenFilter line 43-45: uid = 'mock-user-token-<target-uid>'.replace('mock-user-token-', '') = target-uid
4. Attacker now authenticated as target-uid with ROLE_USER
5. Can read/delete history, contacts, analytics of target user
💥 Impact: Full data access of any user whose uid is known.
✅ Fix: Remove all mock token handling from production code.

## Remediation Roadmap
Remediation Roadmap – Prioritized Action Plan
Finding ID | Severity | Sprint / Timeline | Vulnerability Type | File | Action Required | Owner
AUTH-001 | CRITICAL | Sprint 0 – Immediate (< 24h) | Hardcoded Mock Admin Token | config/FirebaseTokenFilter.java | Remove hardcoded tokens entirely. Use only real Firebase ID-token verification in all environments. | Backend Dev Lead
AUTH-002 | CRITICAL | Sprint 0 – Immediate (< 24h) | Authentication Bypass – Any Token Accepted | config/FirebaseTokenFilter.java | Fail closed: return HTTP 401/503 when Firebase is not configured rather than granting access. | Backend Dev Lead
AUTH-003 | CRITICAL | Sprint 0 – Immediate (< 24h) | Silent Fallback on Token Verification Failure | config/FirebaseTokenFilter.java | On verification failure, clear the security context and return HTTP 401. Never fall back to authenticated state. | Backend Dev Lead
AUTH-004 | HIGH | Sprint 1 – This Sprint (< 1 week) | Wildcard Mock-User Token Accepted | config/FirebaseTokenFilter.java | Remove all mock token logic from production code. Gate dev helpers behind a build profile. | Backend Dev Lead
AUTH-005 | HIGH | Sprint 1 – This Sprint (< 1 week) | Weak OTP – No Rate Limiting / No Expiry | controller/AuthController.java | Add OTP expiry (5 min), max 5 attempts, and account lockout. Consider using a secure token instead of numeric OTP. | Backend Dev Lead
AUTH-006 | HIGH | Sprint 1 – This Sprint (< 1 week) | OTP Leaked to Server Logs | controller/AuthController.java | Never log secrets. Send OTP via a secure email/SMS channel only. | Backend Dev Lead
AUTHZ-001 | HIGH | Sprint 1 – This Sprint (< 1 week) | IDOR – getAuthUserId Falls Back to Hardcoded UID | controller/EmergencyController.java | Return HTTP 401 when the principal cannot be resolved. Never fall back to a default uid. | Backend Dev Lead
AUTHZ-002 | HIGH | Sprint 1 – This Sprint (< 1 week) | IDOR – Client-Supplied userId in SOS Endpoint | controller/EmergencyController.java | Ignore client-supplied userId. Always derive uid from the authenticated session. | Backend Dev Lead
AUTHZ-003 | HIGH | Sprint 1 – This Sprint (< 1 week) | Privilege Escalation via Email Match | config/FirebaseTokenFilter.java | Grant admin via Firebase custom claims only. Never use email-based role assignment. | Backend Dev Lead
INJ-001 | HIGH | Sprint 1 – This Sprint (< 1 week) | Server-Side Request Forgery (SSRF) – TTS Endpoint | controller/TranslationController.java | Whitelist allowed language codes. Validate the lang parameter against an enum before constructing the URL. | Backend Dev
INP-001 | HIGH | Sprint 1 – This Sprint (< 1 week) | Unsanitized Username Logged to Audit Log | controller/AuthController.java | Sanitize log output; strip or escape control characters before logging user input. | Backend Dev
SDE-001 | HIGH | Sprint 1 – This Sprint (< 1 week) | Service Account Key Committed to Source Code | resources/firebase-service-account.json | Add firebase-service-account.json to .gitignore. Inject via environment variable or secret manager at runtime. | DevOps / Backend Dev Lead
SDE-002 | HIGH | Sprint 1 – This Sprint (< 1 week) | Sensitive PII Logged to stdout | controller/HistoryController.java | Remove verbose logging of user content. If logging is needed, use structured masked logging. | DevOps / Backend Dev Lead
SDE-003 | HIGH | Sprint 1 – This Sprint (< 1 week) | User Text Exposed in Translation API Logs | service/TranslationService.java | Log only metadata (language pair, success/failure, latency). Never log user content. | DevOps / Backend Dev Lead
API-001 | HIGH | Sprint 1 – This Sprint (< 1 week) | CORS Wildcard – Allow All Origins | config/SecurityConfig.java | Restrict allowed origins to specific production and staging domains. Never combine wildcard with allowCredentials=true. | Backend Dev Lead
API-002 | HIGH | Sprint 1 – This Sprint (< 1 week) | CSRF Protection Disabled | config/SecurityConfig.java | If REST-only, CSRF disable is acceptable with strict CORS. Fix the CORS wildcard first. | Backend Dev Lead
API-003 | HIGH | Sprint 1 – This Sprint (< 1 week) | @CrossOrigin(origins='*') Annotation Overrides Security Config | controller/TranslationController.java | Remove per-controller @CrossOrigin. Manage all CORS centrally in SecurityConfig. | Backend Dev Lead
AUTH-007 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | Self-Asserted Registration – No UID Validation | controller/AuthController.java | Derive uid exclusively from a verified Firebase ID token; never trust client-supplied uid. | Backend Dev Lead
AUTH-008 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | Password Reset Without OTP Re-Verification | controller/AuthController.java | Use a single-use signed token from the verify step; tie it to the session that completed OTP verification. | Backend Dev Lead
AUTHZ-004 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | IDOR – Delete Contact Without Ownership Check | controller/EmergencyController.java | Verify document ownership before deletion; return 403 if the contact does not belong to the requesting user. | Backend Dev Lead
INJ-002 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | Unvalidated Redirect to External Translation API | service/TranslationService.java | Validate src/tgt against a strict whitelist of ISO 639-1 codes before use in URL. | Backend Dev
INP-002 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | Phone Number Sanitization Insufficient | controller/EmergencyController.java | Validate phone numbers against E.164 format using a library such as libphonenumber. | Backend Dev
INP-003 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | No Input Length Limits on Free-Text Fields | controller/HistoryController.java | Enforce max field lengths (e.g., 2000 chars). Return HTTP 400 for oversized input. | Backend Dev
SDE-004 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | SOS Message Content Logged to stdout | service/TwilioService.java | Replace content logging with '[SMS dispatched to +XX]'. Do not log message body. | DevOps / Backend Dev Lead
SDE-005 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | Mock Credentials Hardcoded in Production Code | controller/AuthController.java | Remove all mock users. Seed test data through a separate test-only configuration class. | DevOps / Backend Dev Lead
API-004 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | Missing Security Headers | config/SecurityConfig.java | Add a SecurityHeadersFilter or configure headers via Spring Security's headers() DSL. | Backend Dev Lead
API-005 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | No Rate Limiting on Any Endpoint | config/SecurityConfig.java | Implement rate limiting via Spring's Resilience4j, Bucket4j, or an API gateway. | Backend Dev Lead
API-006 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | Authorization Header Exposed in CORS | config/SecurityConfig.java | Remove Authorization from exposedHeaders unless there is a specific business need. | Backend Dev Lead
BIZ-001 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | SOS Endpoint – No Rate Limiting / Spam Risk | controller/EmergencyController.java | Enforce a minimum interval (e.g., 60 s) per user per SOS dispatch. Add rate limiting. | Product + Backend Dev
INF-001 | MEDIUM | Sprint 2 – Next Sprint (< 2 weeks) | Placeholder Twilio Credentials as Defaults | resources/application.properties | Use required binding (fail-fast on startup if Twilio credentials are missing or placeholder). Log a clear warning. | DevOps
INP-004 | LOW | Sprint 3 – Backlog (< 1 month) | Missing Email Format Validation on Registration | controller/AuthController.java | Add regex or Bean Validation (@Email) to reject malformed email addresses. | Backend Dev
BIZ-002 | LOW | Sprint 3 – Backlog (< 1 month) | Hardcoded Fake Analytics Data | controller/AdminController.java | Derive all statistics from real Firestore aggregation queries. | Product + Backend Dev
INF-002 | LOW | Sprint 3 – Backlog (< 1 month) | Spring Boot 3.3.0 – Potential Known CVEs | pom.xml | Update to the latest Spring Boot 3.x patch. Monitor CVE databases for Spring ecosystem vulnerabilities. | DevOps

## Dangerous Sinks & Endpoints
Dangerous Data Sinks & Unprotected Endpoints
Endpoints That Should Require Authentication But Do Not (or Have Bypass)
Endpoint | Method | Current Auth | Issue | Risk | Fix
POST /api/auth/verify-otp | POST | None (public) | No rate limit on OTP guess | CRITICAL | Add rate limit + lockout
POST /api/auth/reset-password | POST | None (public) | No rate limit; password change | CRITICAL | Add rate limit + secure token
POST /api/translate | POST | None (public) | Unlimited translation calls | MEDIUM | Add rate limiting
POST /api/tts | POST | None (public) | SSRF risk; no rate limit | HIGH | Whitelist lang; add rate limit
GET /api/health/** | GET | None (public) | May expose server info | LOW | Return minimal health info only
POST /api/auth/forgot-password | POST | None (public) | Email enumeration possible | MEDIUM | Return same response regardless of email existence
All endpoints (bypass) | ALL | Bypassed | AUTH-001/002/003 allow full bypass | CRITICAL | Fix authentication filter logic
User-Controlled Data Reaching Dangerous Sinks
Source (User Input) | Sink (Dangerous Operation) | File | Line | Risk | Fix
Request body: lang param | Google TTS URL construction (SSRF) | TranslationController.java | 67 | HIGH | Whitelist language codes
Request body: text param | Logged to stdout (PII exposure) | TranslationService.java | 186 | HIGH | Remove content logging
Request body: userId | Firestore read: victim's emergency contacts | EmergencyController.java | 207 | HIGH | Use session uid only
Request body: uid (register) | Firestore write: document id = client uid | AuthController.java | 91 | HIGH | Use verified token uid
Request body: username | Audit log (log injection) | AuthController.java | 141 | MEDIUM | Sanitize before logging
Request body: original text | System.out print (PII in logs) | HistoryController.java | 124 | HIGH | Remove content logging
Path var: contact id | Firestore delete without ownership check | EmergencyController.java | 167 | MEDIUM | Verify ownership before delete
Request body: text + lang | External API call to MyMemory (data leakage) | TranslationService.java | 206 | MEDIUM | Privacy notice; sanitize input

## Security Assumptions
Unsafe Security Assumptions Found in Codebase
Assumption Made | Location | Why It Is Unsafe | Real Threat | Correction
Firebase placeholder credentials mean the app is development-only | FirebaseTokenFilter.java – isFirebaseInitialized() check | Placeholder creds are committed to source code. If the container is deployed as-is (CI/CD misconfiguration), all auth is bypassed. | Full authentication bypass in any environment where real credentials are absent | Fail closed: refuse to start or return 503 if Firebase is unconfigured
Mock tokens will only be used by developers | FirebaseTokenFilter.java lines 39–46 | Mock tokens are in version-controlled source code. Any team member, CI log reviewer, or attacker with repo access can use them. | Permanent backdoor into any deployed instance | Remove mock token handling entirely from the auth filter
Only 5 emergency contacts can be added, preventing abuse | EmergencyController.java line 110 | An attacker can create thousands of accounts and each triggers SOS independently; the per-user limit does not prevent platform abuse. | Twilio account credit exhaustion; emergency-contact spam | Add per-IP and per-account SOS rate limiting at the platform level
Email-based admin role is secure because only admins know the email | FirebaseTokenFilter.java line 64 | admin@gesturespeak.com is a predictable email. Combined with the auth bypass, any dev-mode user who registers with this email gets ADMIN. | Privilege escalation to admin role | Grant admin role via Firebase custom claims; never via email string match
Logging user content is safe for debugging | HistoryController.java, TranslationService.java, TwilioService.java | Users may translate sensitive medical, personal, or location information. Log files are often unencrypted and widely accessible. | PII/PHI data breach via log exposure | Log only metadata; never log message content or personal data
Twilio fallback (mock=true) prevents real SMS from being sent | TwilioService.java lines 29–38 | The placeholder string check could fail if env vars are partially set (e.g., non-empty but incorrect sid). Real SMS might be attempted. | Unexpected Twilio API calls or error-triggered data leaks in response bodies | Use a strict environment profile check; require explicit mock=true flag
Client-supplied uid in register is validated by Firebase Auth | AuthController.java line 91 | There is no Firebase ID token verification at registration. Any uid can be written to Firestore. | Data pollution; potential overwrite of existing user profiles | Require a verified Firebase ID token; extract uid server-side only